| Period | Action(s) | Completed - Date |
| --- | --- | --- |
| One Year Before Event | Start to organise Identify someone to be the lead on the event (main event organiser) Identify a group of people that will help to plan and deliver the event (event team) Identify someone to lead on the health and safety elements of the event (Safety Officer) Share out job roles and responsibilities taking into account competency and time Agree an outline event plan Why are you holding the event? What are the main aims? What is the event concept? Venue, insurance, licensing, permissions, dates, timings… Assess numbers of people likely to attend the event Consider the budget you will need to put the event on Investigate suitability of the venue Assess size, facilities and accessibility Consider the impact your event will have on traffic in local area, parking, public transport and any road closures / diversions necessary Contact your relevant local authority The Local Authority event co-ordinator is there to advise and guide you through the process Complete Event Notification Form Available from your local authority event co-ordinator Start to consider your event risk assessment An example and instructions for completing a risk assessment is available in the toolkit supplied by the local authority Event Co-ordinator. Previous experience If this is a repeat event, review last year’s plans and consider any changes that need to be made. Do any issues need addressing? Would you do anything differently? |  |

| 9 Months Before Event | Investigate insurance cover Public liability (most local authorities require a minimum of £5 million) Employers liability Cancellation cover Equipment Think about medical cover for your event and recruit an organisation Prepare Event Management Plan and Site Plan Copies of templates (and example documents) for these plans will be available from your local authority. They are also available on the local authority website. Please see the event toolkit for guidance, supplied by the Event Co-ordinator Consider contractors and equipment that is required for your event Provisionally book any contractors and equipment for your event |  |
| --- | --- | --- |
| 6 Months Before Event | Start writing your event Risk Assessment Seek guidance from your local authority and health and safety professionals and break the assessment down into components of your event. Look into any event licences that are required A temporary events notice (TEN) may be required for licensable activities such as: live/amplified entertainment, sale of alcohol, late night refreshment Confirm Highways Requirements Apply for road closures, parking restrictions, permission to place temporary signs in the highway – minimum notice periods may apply. In most cases 12 weeks’ notice is required for a road closure. Agree all access, exit and public transport arrangements. Apply for any Parking Suspensions Suspension requests for on-street parking bays Suspension requests for off-street parking (liaise with car park operators) Application for these is usually done via completion of the event notification form Confirm bookings Artists, entertainers, stallholders, equipment hire, security Communication Consider how you will advertise your event and whether planning permission is required How you advertise your event may have an impact on attendance Include details in your event management plan |  |
| 3 Months Before Event | Submit your Event Management Plan, Risk Assessment and Site Plan to your local authority These documents should be submitted no later than 3 months before your event as this is the minimum time required for organisations to review the paperwork and put things in place. Check progress of licence applications Recruit Stewards/marshals as necessary Develop Stewards/marshals handbook as necessary Confirm the key roles and responsibilities of the team and circulate this information Pay land hire fee and deposit fee to Local authority Check the insurance, method statements, and risk assessments of any contractors as necessary |  |
| 6 Weeks Before Event | Review your event Risk Assessment Review Event Management Plan, Site Plan and other plans that are deemed necessary Check progress of licence applications |  |

| 1 Month Before Event | Review and finalise your Event Risk Assessment Review and finalise Event Management Plan Evacuation procedures, fire points etc. Contingency plans as identified in the risk assessments Final booking checks Artists, Entertainers, Stallholders, Insurance, Catering, Equipment, Security Organise clean up teams for during and after the event Make arrangements with Local Authority if necessary Train your Team Crowd control, traffic control, emergency procedures, general information, basic fire fighting Distribute steward/marshal handbook once staff have been trained |  |
| --- | --- | --- |
| 1 Week Before Event | If road closures are under the Town Police Clause legislation, put up the official road closure notices (issued by local authority) If road closure is issued under KCC Highways & Transportation legislation, then KCC will send you a notice |  |
| Day Before Event | Check the site It is down to you to make sure that everything is set up properly and there are no hazards to the public. Establish Event Control Ensure you have team member(s) on site to manage the site build Ensure you have security to monitor any equipment overnight Erect any temporary structures and position concessions on your event site Hold a Briefing for your Event Team |  |

| Day of the Event | Hold final team briefing to include stewards / marshals SIA staff Erect temporary road signage in accordance with traffic management plan, signage schedule and working on the highway risk assessment Remove all traffic management as agreed by Kent Highways & Transportation at the end of the event. Ensure waste is disposed of at the site You need to keep the area that you are using clean and remember the litter left by the people that come along is your responsibility! Debrief held to establish any lessons learned or amendments to be made to Event Management Plan for future use. |  |
| --- | --- | --- |
| Day After the Event | Ensure that waste has all been removed including any local advertising Remove all temporary signage and structures Ensure the event site is left in good condition |  |
| Week after the Event | Advise your Local authority on any issues with the event Advise your local authority of any future events |  |